## Sheet1
PROJECT NUMBER | 14
PROJECT NAME | LMS, EdTech Platform Implementation, for online courses
PROJECT MENTOR (sponsor) | Tariq Khan (Eklavya Foundation)
SHEET LINK | https://docs.google.com/spreadsheets/d/1sIHVsbBAiHJD51LNNtB2LDqORrgGZhSRrA07xUTBcT8/edit?usp=sharing
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimated Error | Estimation error %
See Instructions sheet for usage
Week 1 (January 16- January 21) | [8 empty] | Done
Fix meeting with client | Coordination | Virat, Varun | 0.5 | 0.3 | Done |  | 0.2 | 66.6667 | Ongoing
GIT Repository setup | Preparation | Varun | 0.1 | 0.05 | Done |  | 0.05 | 100 | Planned
Client Meeting and MOM-1 Writeup | Coordination | Prajas | 2.5 | 2 | Done | Make sure scoping questions are included | 0.5 | 25
Get account and configure website | Preparation | Varun | 1.5 | 1 | Done |  | 0.5 | 50
Research existing technology | Preparation | Vishnu,Virat | 2 | 1.5 | Done |  | 0.5 | 33.3333
Project synopsis writeup | Documentation | Keerthi, Prajas | 3 | 4 | Done |  | -1 | -25
Identify role owners | Preparation | Varun | 2 |  | Done | Multiple roles are OK - think about role & reponsibility distribution | 2 | #DIV/0!
Team Meeting | Coordination | Varun | 1 | 2 | Done |  | -1 | -50
MoM-1 Write Up | Documentation | Prajas | 1.5 | 1 | Done
Status tracker | Documentation | Varun | 1 |  | Done |  | 1 | #DIV/0!
Week 2 (January 22 - January 28) | [6 empty] | 0 | #DIV/0!
Website Design | Preparation | Virat, Vishnu | 3 | 3.5 | Done |  | -0.5 | -14.2857
Project Planner Discussion & Writeup | Documentation | Varun | 3 | 4 | Done | This is critical to project success | -1 | -25
Client Meeting | Coordination | Virat | 1.5 | 1 | Done | Discussion about the overall workflow of the website.What are the different types of users and what all views would be accessible to different users. Clarified the project requirements | 0.5 | 50
Status tracker | Documentation | Varun | 1 | 1 | Done |  | 0 | 0
MOM-2 Writeup | Documentation | Keerthi | 1 | 1 | Done |  | 0 | 0
Week 3 (January 29 - February 4) | [6 empty] | 0 | #DIV/0!
Requirement Analysis | Preparation | Virat,Varun | 4 | 4 | Done | We did Requirement Analysis to see how We can complete the requirements using least not fo | 0 | 0
Project Research | Preparation | Vishnu | 2 | 2 | Done |  | 0 | 0
Tool Analysis | Preparation | Keerthi | 2 | 1.5 | Done |  | 0.5 | 33.3333
Team Meeting | Coordination | Prajas | 1 | 1.5 | Done |  | -0.5 | -33.3333
Status tracker | Documentation | Varun | 1 | 1 | Done |  | 0 | 0
Week 4 (Feburary 5 - February 11) | [6 empty] | 0 | #DIV/0!
SRS Writeup | Documentation | Virat | 3 | 3 | Done |  | 0 | 0
WorkFlow Analysis | Preparation | Varun,Prajas | 4 | 4.5 | Done |  | -0.5 | -11.1111
Synopsis Update | Documentation | Keerthi | 2 | 1.5 | Done |  | 0.5 | 33.3333
Team Meeting | Coordination | Vishnu | 1 | 1 | Done |  | 0 | 0
MOM-3 | Documentation | Vishnu | 1.5 | 1 | Done
Status Tracker | Documentation | Varun | 1 | 1 | Done |  | 0 | 0
Week 5 (Feburary 12 - February 18) | [6 empty] | 0 | #DIV/0!
Backend Set Up Phase 2 | Preparation | Varun | 4 | 3.5 | Done |  | 0.5 | 14.2857
SRS Update | Documentation | Virat | 2 | 1.5 | Done |  | 0.5 | 33.3333
Schema Setup-1 | Preparation | Prajas,Keerthi | 2.5 | 3 | Done
Client Database Setup | Preparation | Varun | 0.5 | 0.5 | Done
Frontend Starting | Preparation | Virat,Vishnu | 3 | 3 | Done |  | 0 | 0
Status Tracker | Documentation | Varun | 1 | 1 | Done
Week 6 (Feburary 19 - February 25)
Backend - 2 | Preparation | Varun | 6 | 5.5 | Done
Postman Testing - 1 | Preparation | Prajas,Keerthi | 4 | 4.5 | Done
Frontend | Preparation | Virat,Vishnu | 5 | 5 | Done
Database Fixing | Preparation | Varun | 1 | 1 | Done
Status Tracker | Documentation | Varun | 1 | 1 | Done
Week 7 (Feburary 26 - March 4)
Backend Phase 2 Complete | Preparation | Varun | 4.5 | 4 | Done
Postman Testing - 2 | Preparation | Prajas,Keerthi | 3 | 3.5 | Done
Frontend Phase 2 Complete | Preparation | Virat,Vishnu | 4 | 4 | Done
Status Tracker | Documentation | Varun | 1 | 1 | Done
Week 8 (March 5 - March 11)
Phase-2 Document | Documentation | Keerthi | 1 | 1.5 | Done
Testing | Preparation | Vishnu | 2.5 | 3 | Done
Backend Phase 3 | Preparation | Varun | 3.5 | 3 | Done
Frontend Phase 3 | Preparation | Virat | 4 | 3 | Done
Design Doc | Documentation | Keerthi,Prajas | 3 | 3.5 | Done
MOM 5 | Documentation | Prajas | 2 | 1.5 | Done
Status Tracker | Documentation | Varun | 1 | 1 | Done
Week 9 (March 12 - March 18)
Backend Phase 3 | Preparation | Prajas,Keerthi | 5 | 4 | Done
Frontend Phase 3 | Preparation | Virat,Vishnu | 4.5 | 4 | Done
Postman Testing | Preparation | Varun | 4 | 4 | Done
Status Tracker | Documentation | Varun | 1 | 1 | Done
Week 10 (March 19 - March 25)
Postman Testing | Preparation | Varun | 4 | 4 | Done
Teacher Routes and Controlled | Preparation | Prajas,Keerthi | 3.5 | 4 | Done
Frontend Admin Console | Preparation | Virat,Vishnu | 4 | 3.5 | Done
MOM 6 | Documentation | Virat | 1 | 1 | Done
Status Tracker | Documentation | Varun | 1 | 1 | Done
Week 11 (March 26 - April 1)
Teacher Routes | Preparation | Prajas, Keerthi | 5 | 4 | Done
Learning Docker | Preparation | Varun | 4 | 3.5 | Done
Frontend for Teacher View | Preparation | Virat, Vishnu | 6 | 5 | Done
Status Tracker | Documentation | Varun | 1 | 1 | Done
Week 12 (April 2 - April 8)
Learning Deployement | Preparation | Varun | 5 | 4 | Done
Postman Testing for Teacher | Preparation | Prajas, Keerthi | 4 | 4 | Done
Frontend Testing | Preparation | Virat, Vishnu | 4 | 3.5 | Done
Testing Doc | Documentation | Varun, Virat | 5 | 4 | Done
Status Tracker | Documentation | Varun | 1 | 1 | Done
Week 13 (April 9 - April 15)
Docker Optimization | Preparation | Varun | 3 | 3 | Done
Backend Testing | Preparation | Prajas,Keerthi | 4 | 4 | Done
Frontend Tetsing | Preparation | Virat,Vishnu | 4 | 4 | Done
Status Tracker | Preparation | Varun | 1 | 1 | Done
Week 13 (April 16 - April 22)
Docs Updation | Documentation | Keerthi | 3 | 2.5 | Done
Data Addition | Preparation | Virat | 4 | 4.5 | Done
Overall Testing | Preparation | Prajas,Vishnu | 4 |  | Planned
Presentation | Preparation | Varun | 4 |  | Planned
Status Tracker | Documentation | Varun | 1 |  | Planned